## Sheet1
ElementName | section_ID | loc_from | loc_to | area | TreatmentName | TreatmentCost | TreatmentPeriod | DecisionCode | Comment
MASTERTON CASTLEPOINT ROAD_15603 | 142 | 15603 | 17224 | 11022.8 | Rehab_CS_RM | 589894.2 | 2 | accept | Condition data in RAMM is inaccurate
NEWALL PLACE_5 | 279 | 5 | 74 | 627.9 | Preseal_CS | 65929.5 | 2 | modify | Repair methodology to be re-considered- reduce actual cost
YORK STREET_0 | 371 | 0 | 89 | 1139.2 | Preseal_CS | 17088 | 2 | accept | Agree
INTERMEDIATE STREET_6 | 163 | 6 | 544 | 5541.4 | Preseal_CS | 41560.5 | 2 | accept
HOSKING PLACE_4 | 159 | 4 | 66 | 334.8 | Preseal_CS | 25110 | 2 | modify | MDC to check with services programme and confirm
COLE STREET_943 | 65 | 943 | 1506 | 3997.3 | Preseal_CS | 29979.75 | 2 | accept | Agree
GEORGE HERON PLACE_6 | 411 | 6 | 62 | 504 | Preseal_CS | 52920 | 2 | accept | Agree
KIBBLEWHITE ROAD_5 | 104 | 5 | 643 | 3764.2 | Preseal_CS | 28231.5 | 2 | modify | MDC to look into drainage improvements on rural side
RAILWAY CRESCENT_7 | 321 | 7 | 368 | 3501.7 | ChipSeal_H | 34316.66 | 3 | push_out | RP 0-160 existing surface is AC RP 160-368 existing surface is CS, Push both sections out 8yrs
RAILWAY CRESCENT_7 | 321 | 7 | 368 | 3501.7 | Preseal_CS | 26262.75 | 2 | push_out | RP 0-160 Existing surface is AC, RP 160-368 existing surface is CS, Push pre-seal on both sections out 7 yrs
KITCHENER STREET_6 | 203 | 6 | 528 | 6525 | Preseal_CS | 48937.5 | 2 | modify | Extend Kitchener St section right up to Gordon St
KITCHENER STREET_6 | 203 | 6 | 528 | 6525 | ChipSeal_H | 63945 | 3 | modify | Extend Kitchener St section right up to Gordon St
MANUKA STREET_6 | 245 | 6 | 504 | 4482 | Preseal_CS | 67230 | 2 | accept | Agree
MATAI STREET_6 | 259 | 6 | 206 | 2520 | Preseal_CS | 18900 | 2 | accept
TITOKI STREET_6 | 352 | 6 | 273 | 1815.6 | Preseal_CS | 13617 | 4 | modify | Bring forward to 2025/26 preseal alongside RP 335-620
TITOKI STREET_335 | 352 | 335 | 620 | 1938 | Preseal_AC | 18411 | 2 | modify | Resurface will need to be CS in 26/27 - forced trigger, Combine with RP 0-273 CS section
KILMORY LANE_370 | 440 | 370 | 398 | 168 | Preseal_AC | 22344 | 2 | push_out | Push out 8 yrs
QUEEN STREET_452 | 315 | 452 | 527 | 1087.5 | Rehab_AC_UM | 313200 | 2 | push_out | Funding allocated elsewhere
PERRY STREET CBD_4 | 303 | 4 | 115 | 1110 | Preseal_AC | 10545 | 2 | modify | Rehab
BANNISTER STREET_6 | 21 | 6 | 115 | 1068.2 | Preseal_AC | 20295.8 | 2 | modify | Rehab
CHAPEL STREET S.L. (LONGS)_6 | 375 | 6 | 106 | 540 | Preseal_AC | 15390 | 2 | modify | Move to year 3
CHAPEL STREET S.L. (TRUSTBANK)_6 | 374 | 6 | 100 | 376 | Preseal_AC | 7144 | 2 | modify | Move to year 3
CRICKET STREET_7 | 85 | 7 | 153 | 803 | Preseal_CS | 18067.5 | 2 | modify | Move to year 3 MDC to carry out stormwater improvements on intersection to Park St in year 2
QUEEN STREET_527 | 315 | 527 | 711 | 2576 | Preseal_AC | 48944 | 2 | accept
CRICKET STREET_288 | 85 | 288 | 348 | 384 | Preseal_CS | 2880 | 2 | push_out | Push out 10 yrs, MDC to update top surface in RAMM
MASTERTON STRONVAR ROAD_6 | 146 | 6 | 28 | 165 | Preseal_AC | 21945 | 2 | modify | Committed section in year 3 rehab
WATSONS ROAD_3365 | 308 | 3365 | 3750 | 1540 | Preseal_CS | 11550 | 2 | modify | Trigger the whole road
WATSONS ROAD_3365 | 308 | 3365 | 3750 | 1540 | ChipSeal_H | 15092 | 3 | modify | Trigger the whole road
TE ORE ORE BIDEFORD ROAD_8447 | 270 | 8447 | 8673 | 1356 | Preseal_CS | 20340 | 2 | push_out | Push to next NLTP
TE ORE ORE BIDEFORD ROAD_13698 | 270 | 13698 | 14039 | 2046 | Preseal_CS | 30690 | 2 | modify | Push out to year three, MDC to look at drainage improvement work
OPAKI KAIPARORO ROAD_24106 | 208 | 24106 | 24725 | 3775.9 | Preseal_CS | 28319.25 | 2 | accept
MASTERTON CASTLEPOINT ROAD_39742 | 142 | 39742 | 39800 | 382.8 | Rehab_CS_RM | 66990 | 2 | push_out | Push out 5yrs. Pavement has some rutting but can last another 5yrs
DIXON STREET_647 | 95 | 647 | 1648 | 14814.8 | Preseal_CS | 333333 | 3 | push_out | Why is this section being triggered - surface is less than 8yrs old
RENALL STREET_955 | 324 | 955 | 1600 | 8643 | Preseal_AC | 164217 | 3 | push_out | Push out 10 yrs - Mostly reflective cracking
UPPER PLAIN ROAD_0 | 288 | 0 | 475 | 5747.5 | Preseal_CS | 43106.25 | 3 | accept
SOUTH ROAD URBAN_0 | 338 | 0 | 958 | 12454 | Preseal_CS | 93405 | 3 | accept
COCKBURN STREET_29 | 61 | 29 | 136 | 1786.9 | Rehab_CS_UM | 312707.5 | 3 | modify | Preseal & reseal treatment
YORK STREET_89 | 371 | 89 | 458 | 4797 | Preseal_CS | 35977.5 | 3 | accept
SOLWAY CRESCENT_359 | 335 | 359 | 926 | 6237 | SecondCoat | 61122.6 | 3 | accept
SOLWAY CRESCENT_926 | 335 | 926 | 1136 | 2310 | SecondCoat | 22638 | 3 | accept
STONELEIGH DRIVE_7 | 446 | 7 | 297 | 2175 | SecondCoat | 21315 | 3 | accept
MITRE WAY_4 | 462 | 4 | 180 | 1320 | SecondCoat | 12936 | 3 | accept
OLD ORCHARD ROAD_6 | 464 | 6 | 143 | 808.3 | SecondCoat | 7921.34 | 3 | push_out | This is not a 2nd coat - RAMM data incorrect
ANDREWS STREET_0 | 11 | 0 | 466 | 2889.2 | SecondCoat | 28314.16 | 3 | push_out | This is not a 2nd coat - RAMM data incorrect
ANDREWS STREET_466 | 11 | 466 | 532 | 409.2 | SecondCoat | 4010.16 | 3 | push_out | This is not a 2nd coat - RAMM data incorrect
TARANAKI STREET_325 | 346 | 325 | 595 | 2430 | SecondCoat | 23814 | 3 | accept
LEES PAKARAKA ROAD_2399 | 116 | 2399 | 3740 | 8046 | SecondCoat | 78850.8 | 3 | accept
TE WHITI ROAD_4955 | 144 | 4955 | 5206 | 1506 | SecondCoat | 14758.8 | 3 | accept
LEES PAKARAKA ROAD_73 | 116 | 73 | 1120 | 5235 | SecondCoat | 51303 | 3 | accept
MASTERTON CASTLEPOINT ROAD_7553 | 142 | 7553 | 7840 | 2009 | SecondCoat | 19688.2 | 3 | accept
MASTERTON CASTLEPOINT ROAD_10750 | 142 | 10750 | 10951 | 1246.2 | Rehab_CS_RM | 218085 | 3 | push_out | Re-look in year 7
MASTERTON CASTLEPOINT ROAD_11809 | 142 | 11809 | 11900 | 564.2 | Rehab_CS_RM | 98735 | 3 | modify | Move to year 4 - check funding allocation in model for rehabs
MASTERTON CASTLEPOINT ROAD 2_61123 | 398 | 61123 | 61486 | 1996.5 | Rehab_CS_RM | 349387.5 | 3 | modify | Move to year 4 - check fund allocation for rehabs in model
MASTERTON CASTLEPOINT ROAD 2_54983 | 398 | 54983 | 55594 | 3910.4 | SecondCoat | 38321.92 | 3 | accept
TINUI VALLEY ROAD_5140 | 282 | 5140 | 7120 | 9504 | SecondCoat | 93139.2 | 3 | accept
ANNEDALE ROAD_203 | 8 | 203 | 311 | 367.2 | Preseal_CS | 8262 | 3 | modify | MDC to field validate
BRUCE STREET_6 | 37 | 6 | 114 | 1674 | Preseal_AC | 15903 | 3 | push_out | Push out 10yes -brick crossings causing fault triggers
WESTMERE ROAD_3460 | 318 | 3460 | 4420 | 5760 | SecondCoat | 56448 | 3 | accept
TE ORE ORE ROAD_1096 | 404 | 1096 | 2287 | 16316.7 | ChipSeal_P | 91826.7 | 1 | accept
TE ORE ORE ROAD_2287 | 404 | 2287 | 2347 | 420 | Rehab_AC_RM | 122040 | 1 | accept
TE ORE ORE BIDEFORD ROAD_5 | 270 | 5 | 50 | 315 | Rehab_AC_RM | 149040 | 1 | accept
MASTERTON CASTLEPOINT ROAD_0 | 142 | 0 | 45 | 328.5 | Rehab_AC_RM | 54360 | 1 | accept
WAVELL CRESCENT_6 | 363 | 6 | 465 | 4131 | ChipSeal_P | 21758.2 | 1 | accept
GORT PLACE_5 | 125 | 5 | 64 | 413 | ChipSeal_P | 3068.6 | 1 | accept
TE ORE ORE ROAD_740 | 404 | 740 | 1096 | 4877.2 | ChipSeal_P | 12169.9 | 1 | accept
TE ORE ORE ROAD_356 | 404 | 356 | 740 | 5376 | ChipSeal_P | 25993.9 | 1 | accept
TE ORE ORE ROAD_40 | 404 | 40 | 296 | 3584 | ChipSeal_P | 9689.9 | 1 | accept
DIXON STREET_323 | 95 | 323 | 647 | 4212 | Rehab_AC_UH | 1097044.8 | 1 | accept
WRIGLEY STREET_7 | 370 | 7 | 350 | 4802 | ChipSeal_P | 20512 | 1 | accept
DIXON STREET_1648 | 95 | 1648 | 2267 | 8356.5 | ChipSeal_P | 41896.5 | 1 | accept
HIGH STREET (SH2)_0 | 147 | 0 | 176 | 2464 | ChipSeal_P | 14288.4 | 1 | accept
WALTONS AVE_0 | 361 | 0 | 95 | 1235 | ChipSeal_P | 6739 | 1 | accept
BLEDISLOE STREET_10 | 33 | 10 | 296 | 2631.2 | ChipSeal_P | 14721.1 | 1 | accept
FREYBERG STREET_5 | 119 | 5 | 291 | 2574 | ChipSeal_P | 15093.1 | 1 | accept
HOBSON PLACE_5 | 153 | 5 | 74 | 634.8 | ChipSeal_P | 3713.8 | 1 | accept
FERGUSSON STREET_5 | 107 | 5 | 479 | 4408.2 | ChipSeal_P | 25827 | 1 | accept
HARLEY STREET_6 | 137 | 6 | 1228 | 15152.8 | ChipSeal_P | 143150 | 1 | accept
JELLICOE PLACE_5 | 173 | 5 | 74 | 621 | ChipSeal_P | 4478.9 | 1 | accept
GIMSON STREET_419 | 419 | 419 | 809 | 3549 | ChipSeal_P | 20007 | 1 | accept
CRAIGMILLAR STREET_4 | 448 | 4 | 469 | 4185 | ChipSeal_P | 24610.4 | 1 | accept
WYCLIFFE PLACE_5 | 454 | 5 | 227 | 1998 | ChipSeal_P | 12367.6 | 1 | accept
BANNISTER STREET_130 | 21 | 130 | 925 | 11130 | ChipSeal_P | 59398.9 | 1 | accept
WORKSOP ROAD_140 | 368 | 140 | 525 | 5621 | ChipSeal_P | 32153.5 | 1 | accept
WORKSOP ROAD_525 | 368 | 525 | 922 | 5796.2 | ChipSeal_P | 32907.1 | 1 | accept
LOOPLINE_13 | 124 | 13 | 1956 | 10880.8 | ChipSeal_P | 68801.9 | 1 | accept
PAIERAU ROAD_293 | 214 | 293 | 993 | 4900 | ChipSeal_P | 28611.3 | 1 | accept
PAIERAU ROAD_993 | 214 | 993 | 2493 | 10500 | ChipSeal_P | 66506.3 | 1 | accept
BLUFF RANGITUMAU ROAD_4 | 20 | 4 | 1299 | 7640.5 | ChipSeal_P | 38482.3 | 1 | accept
BLUFF RANGITUMAU ROAD_1299 | 20 | 1299 | 2181 | 5292 | ChipSeal_P | 20926.1 | 1 | accept
BLUFF RANGITUMAU ROAD_2785 | 20 | 2785 | 3288 | 3018 | ChipSeal_P | 20926.1 | 1 | accept
WHANGAEHU VALLEY ROAD_6600 | 405 | 6600 | 6800 | 1420 | ChipSeal_P | 7860 | 1 | accept
WHANGAEHU VALLEY ROAD_6800 | 405 | 6800 | 7000 | 1420 | ChipSeal_P | 6481.6 | 1 | accept
WHANGAEHU VALLEY ROAD_7000 | 405 | 7000 | 8330 | 9443 | ChipSeal_P | 48758.1 | 1 | accept
DITTON ROAD_4 | 52 | 4 | 667 | 2519.4 | ChipSeal_P | 14617.9 | 1 | accept
WHANGAEHU VALLEY ROAD_8330 | 405 | 8330 | 9280 | 6080 | ChipSeal_P | 36872.8 | 1 | accept
WHANGAEHU VALLEY ROAD_9280 | 405 | 9280 | 9416 | 816 | ChipSeal_P | 4730.1 | 1 | accept
TE ORE ORE BIDEFORD ROAD_19589 | 270 | 19589 | 20108 | 3114 | ChipSeal_P | 17247.7 | 1 | accept
MASTERTON CASTLEPOINT ROAD_3932 | 142 | 3932 | 5260 | 8897.6 | ChipSeal_P | 41993.4 | 1 | accept
MASTERTON CASTLEPOINT ROAD_10168 | 142 | 10168 | 10260 | 598 | Rehab_AC_RM | 64800 | 1 | accept
MASTERTON CASTLEPOINT ROAD_13062 | 142 | 13062 | 13183 | 750.2 | Rehab_AC_RM | 139986 | 1 | accept
MASTERTON CASTLEPOINT ROAD_14283 | 142 | 14283 | 15603 | 8184 | ChipSeal_P | 38424.2 | 1 | accept
MASTERTON CASTLEPOINT ROAD_17224 | 142 | 17224 | 17775 | 3746.8 | Rehab_CS_RM | 560732.2 | 1 | accept
MASTERTON CASTLEPOINT ROAD_23300 | 142 | 23300 | 23890 | 4012 | Rehab_CS_RM | 318756.2 | 1 | accept
BLAIRLOGIE LANGDALE ROAD_2844 | 18 | 2844 | 3742 | 6286 | ChipSeal_P | 31288.5 | 1 | accept
BUTE ROAD_1884 | 32 | 1884 | 2140 | 819.2 | Rehab_CS_RM | 161030.8 | 1 | accept
MASTERTON CASTLEPOINT ROAD 2_48906 | 398 | 48906 | 49847 | 6210.6 | ChipSeal_P | 28998.4 | 1 | accept
MASTERTON CASTLEPOINT ROAD 2_57460 | 398 | 57460 | 59910 | 13475 | ChipSeal_P | 62750.7 | 1 | accept
MATAIKONA ROAD_3902 | 148 | 3902 | 4299 | 1588 | ChipSeal_P | 7462.8 | 1 | accept
MATAIKONA ROAD_4299 | 148 | 4299 | 4514 | 860 | ChipSeal_P | 3990.9 | 1 | accept
MATAIKONA ROAD_11268 | 148 | 11268 | 11370 | 469.2 | ChipSeal_P | 2147.1 | 1 | accept
MATAIKONA ROAD_12493 | 148 | 12493 | 12635 | 511.2 | ChipSeal_P | 2341 | 1 | accept
MASTERTON STRONVAR ROAD_21912 | 146 | 21912 | 22600 | 4816 | ChipSeal_P | 26668.3 | 1 | accept
OPAKI KAIPARORO ROAD_13310 | 208 | 13310 | 13925 | 4059 | ChipSeal_P | 19694.1 | 1 | accept
WHANGAEHU VALLEY ROAD_11300 | 405 | 11300 | 12623 | 7938 | ChipSeal_P | 79380 | 2 | accept
WHANGAEHU VALLEY ROAD_12623 | 405 | 12623 | 13900 | 7662 | ChipSeal_P | 76620 | 2 | accept
WHANGAEHU VALLEY ROAD_13900 | 405 | 13900 | 14200 | 1800 | ChipSeal_P | 18000 | 2 | accept
WHANGAEHU VALLEY ROAD_14285 | 405 | 14285 | 15235 | 5700 | ChipSeal_P | 57000 | 2 | accept
WHANGAEHU VALLEY ROAD_14200 | 405 | 14200 | 14285 | 510 | ChipSeal_P | 5100 | 2 | accept
WHANGAEHU VALLEY ROAD_15235 | 405 | 15235 | 15800 | 3390 | ChipSeal_P | 33900 | 2 | accept
WHANGAEHU VALLEY ROAD_15800 | 405 | 15800 | 16300 | 3000 | ChipSeal_P | 30000 | 2 | accept
TE ORE ORE BIDEFORD ROAD_17970 | 270 | 17970 | 19330 | 7208 | ChipSeal_P | 81600 | 2 | accept
TE ORE ORE BIDEFORD ROAD_7020 | 270 | 7020 | 8392 | 8232 | ChipSeal_P | 1120 | 2 | accept
TE ORE ORE BIDEFORD ROAD_4616 | 270 | 4616 | 7020 | 17068.4 | ChipSeal_P | 168280 | 2 | accept
TE ORE ORE BIDEFORD ROAD_50 | 270 | 50 | 2086 | 14252 | ChipSeal_P | 142870 | 2 | accept
MASTERTON CASTLEPOINT ROAD_10951 | 142 | 10951 | 11420 | 2907.8 | Rehab_CS_RM | 290605 | 2 | accept
MASTERTON CASTLEPOINT ROAD_11900 | 142 | 11900 | 12330 | 2666 | Rehab_CS_RM | 407009.4 | 2 | accept
MASTERTON CASTLEPOINT ROAD_12330 | 142 | 12330 | 12501 | 1060.2 | Rehab_CS_RM | 407009.4 | 2 | accept
MASTERTON CASTLEPOINT ROAD_12880 | 142 | 12880 | 13062 | 1128.4 | ChipSeal_P | 32100 | 2 | accept
MASTERTON CASTLEPOINT ROAD_13183 | 142 | 13183 | 13800 | 3825.4 | ChipSeal_P | 32100 | 2 | accept
MASTERTON CASTLEPOINT ROAD_18663 | 142 | 18663 | 19442 | 5297.2 | Rehab_CS_RM | 550765.6 | 2 | accept
BLAIRLOGIE LANGDALE ROAD_3742 | 18 | 3742 | 4080 | 2366 | ChipSeal_P | 29190 | 2 | accept
BLAIRLOGIE LANGDALE ROAD_4080 | 18 | 4080 | 6380 | 16100 | ChipSeal_P | 161000 | 2 | accept
BLAIRLOGIE LANGDALE ROAD_6380 | 18 | 6380 | 8311 | 13517 | ChipSeal_P | 35000 | 2 | accept
HOMEWOOD ROAD_1655 | 90 | 1655 | 3280 | 9750 | ChipSeal_P | 97500 | 2 | accept
BUTE ROAD_8 | 32 | 8 | 1296 | 6440 | Rehab_CS_RM | 481185.6 | 2 | accept
MASTERTON CASTLEPOINT ROAD_29550 | 142 | 29550 | 29918 | 2502.4 | ChipSeal_P | 23628 | 2 | accept
MASTERTON CASTLEPOINT ROAD_29918 | 142 | 29918 | 30596 | 4474.8 | ChipSeal_P | 44748 | 2 | accept
MASTERTON CASTLEPOINT ROAD_30596 | 142 | 30596 | 30700 | 686.4 | ChipSeal_P | 6864 | 2 | accept
MASTERTON CASTLEPOINT ROAD_30700 | 142 | 30700 | 31550 | 5610 | ChipSeal_P | 56100 | 2 | accept
MASTERTON CASTLEPOINT ROAD_31550 | 142 | 31550 | 31715 | 1089 | ChipSeal_P | 10890 | 2 | accept
MASTERTON CASTLEPOINT ROAD_31715 | 142 | 31715 | 32287 | 3775.2 | ChipSeal_P | 37752 | 2 | accept
MASTERTON CASTLEPOINT ROAD_32287 | 142 | 32287 | 33055 | 5068.8 | ChipSeal_P | 50688 | 2 | accept
MASTERTON CASTLEPOINT ROAD_33055 | 142 | 33055 | 33282 | 1475.5 | ChipSeal_P | 12210 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_45464 | 398 | 45464 | 46522 | 6136.4 | ChipSeal_P | 61364 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_46522 | 398 | 46522 | 48906 | 15734.4 | ChipSeal_P | 101500 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_49847 | 398 | 49847 | 50531 | 4514.4 | ChipSeal_P | 45144 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_50531 | 398 | 50531 | 50827 | 1894.4 | ChipSeal_P | 19536 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_50827 | 398 | 50827 | 51958 | 7238.4 | ChipSeal_P | 72384 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_51958 | 398 | 51958 | 52135 | 1132.8 | ChipSeal_P | 11328 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_52135 | 398 | 52135 | 52389 | 1625.6 | ChipSeal_P | 16256 | 2 | accept
TE WHITI ROAD_3030 | 144 | 3030 | 3710 | 4080 | ChipSeal_P | 40800 | 2 | accept
TE WHITI ROAD_3710 | 144 | 3710 | 3990 | 1680 | ChipSeal_P | 16800 | 2 | accept
TE WHITI ROAD_3990 | 144 | 3990 | 4340 | 2100 | ChipSeal_P | 21000 | 2 | accept
TE WHITI ROAD_4340 | 144 | 4340 | 4955 | 3690 | ChipSeal_P | 36900 | 2 | accept
TE WHITI ROAD_5206 | 144 | 5206 | 5319 | 678 | ChipSeal_P | 6780 | 2 | accept
TE WHITI ROAD_6030 | 144 | 6030 | 7670 | 9840 | ChipSeal_P | 98400 | 2 | accept
TE WHITI ROAD_8200 | 144 | 8200 | 9099 | 5394 | ChipSeal_P | 53940 | 2 | accept
TE WHITI ROAD_10110 | 144 | 10110 | 10817 | 4242 | ChipSeal_P | 42420 | 2 | accept
HEREWINI STREET_6 | 143 | 6 | 305 | 4335.5 | ChipSeal_P | 43355 | 2 | accept
HEREWINI STREET_305 | 143 | 305 | 346 | 594.5 | ChipSeal_P | 5950 | 2 | accept
POWNALL STREET_0 | 309 | 0 | 579 | 6484.8 | ChipSeal_P | 38077.6 | 2 | accept
POWNALL STREET_579 | 309 | 579 | 775 | 2312.8 | ChipSeal_P | 7674.4 | 2 | accept
QUEEN STREET_976 | 315 | 976 | 1170 | 2716 | ThinAC_P | 135800 | 2 | accept | note: is dependent on water main renewal
QUEEN STREET_847 | 315 | 847 | 976 | 1806 | ThinAC_P | 90300 | 2 | accept | note: is dependent on water main renewal
QUEEN STREET_711 | 315 | 711 | 847 | 1904 | ThinAC_P | 95200 | 2 | accept | note: is dependent on water main renewal
DREYERS ROCK ROAD_4707 | 60 | 4707 | 6585 | 11268 | ChipSeal_P | 112680 | 3 | accept
DREYERS ROCK ROAD_3500 | 60 | 3500 | 4707 | 7242 | ChipSeal_P | 72420 | 3 | accept
DREYERS ROCK ROAD_2745 | 60 | 2745 | 3500 | 4530 | ChipSeal_P | 12180 | 3 | accept
DREYERS ROCK ROAD_2352 | 60 | 2352 | 2745 | 2358 | Rehab_CS_RM | 200825.8 | 3 | accept
DREYERS ROCK ROAD_1600 | 60 | 1600 | 2352 | 4512 | ChipSeal_P | 23880 | 3 | accept
DREYERS ROCK ROAD_1183 | 60 | 1183 | 1600 | 2502 | Rehab_CS_RM | 176913.8 | 3 | accept
MASTERTON CASTLEPOINT ROAD_1620 | 142 | 1620 | 2140 | 3744 | Rehab_CS_RM | 516880 | 3 | accept
MASTERTON CASTLEPOINT ROAD_2140 | 142 | 2140 | 2473 | 2397.6 | Rehab_CS_RM | 330960 | 3 | accept
MASTERTON CASTLEPOINT ROAD_2473 | 142 | 2473 | 2538 | 435.5 | Rehab_AC_RM | 114660 | 3 | accept
WESTBUSH ROAD_5 | 316 | 5 | 3653 | 21888 | ChipSeal_P | 222528 | 3 | accept
PAIERAU ROAD_7052 | 214 | 7052 | 7734 | 4774 | Rehab_CS_RM | 440216 | 3 | accept
MASTERTON CASTLEPOINT ROAD_9164 | 142 | 9164 | 9688 | 3510.8 | Rehab_CS_RM | 210975.8 | 3 | accept
MASTERTON CASTLEPOINT ROAD_9688 | 142 | 9688 | 10025 | 2257.9 | SecondCoat | 22127.42 | 3 | accept
MASTERTON CASTLEPOINT ROAD_10025 | 142 | 10025 | 10168 | 929.5 | SecondCoat | 9109.1 | 3 | accept
MASTERTON CASTLEPOINT ROAD_10260 | 142 | 10260 | 10750 | 3038 | SecondCoat | 29772.4 | 3 | accept
WATSONS ROAD_7 | 308 | 7 | 3365 | 13432 | Preseal_CS | 302220 | 4 | modify | see year 2 comment bring forward to year 2
TOTARA STREET_715 | 353 | 715 | 917 | 2545.2 | Rehab_CS_UH | 699930 | 4 | modify | change to AC surfacing
DIXON STREET_43 | 95 | 43 | 323 | 4060 | Preseal_AC | 38570 | 4 | push_out | RAMM data not correct update surface life needed for AC layer
TE WHITI ROAD_1185 | 144 | 1185 | 2059 | 5244 | Rehab_CS_RM | 917700 | 4 | accept
TE WHITI ROAD_498 | 144 | 498 | 1185 | 4465.5 | Rehab_CS_RM | 781462.5 | 4 | accept
BLAIRLOGIE LANGDALE ROAD_8311 | 18 | 8311 | 13037 | 33082 | ChipSeal_P | 324203.6 | 4 | accept
MASTERTON CASTLEPOINT ROAD_39742 | 142 | 39742 | 39800 | 382.8 | SecondCoat | 3751.44 | 4 | accept
MATAIKONA ROAD_3220 | 148 | 3220 | 3902 | 3410 | SecondCoat | 33418 | 4 | accept
MASTERTON CASTLEPOINT ROAD_1620 | 142 | 1620 | 2140 | 3744 | SecondCoat | 36691.2 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_2140 | 142 | 2140 | 2473 | 2397.6 | SecondCoat | 23496.48 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_10951 | 142 | 10951 | 11420 | 2907.8 | SecondCoat | 28496.44 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_11900 | 142 | 11900 | 12330 | 2666 | SecondCoat | 26126.8 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_12330 | 142 | 12330 | 12501 | 1060.2 | SecondCoat | 10389.96 | 4 | push_out

## committeds
file_section_id | section_name | file_loc_from | file_loc_to | file_lane_name | area_m2 | elem_index | treatment | period_calendar | treatment_cost | treatment_qty | treatment_comment | treatment_reason
142 | MASTERTON CASTLEPOINT ROAD_15603 | 15603 | 17224 | All | 11022.8 |  | Rehab_CS_RM | 2025 | 589894.2 |  | accepted as committed after model validation | Condition data in RAMM is inaccurate
371 | YORK STREET_0 | 0 | 89 | All | 1139.2 |  | Preseal_CS | 2025 | 17088 |  | accepted as committed after model validation | Agree
163 | INTERMEDIATE STREET_6 | 6 | 544 | All | 5541.4 |  | Preseal_CS | 2025 | 41560.5 |  | accepted as committed after model validation
65 | COLE STREET_943 | 943 | 1506 | All | 3997.3 |  | Preseal_CS | 2025 | 29979.75 |  | accepted as committed after model validation | Agree
411 | GEORGE HERON PLACE_6 | 6 | 62 | All | 504 |  | Preseal_CS | 2025 | 52920 |  | accepted as committed after model validation | Agree
245 | MANUKA STREET_6 | 6 | 504 | All | 4482 |  | Preseal_CS | 2025 | 67230 |  | accepted as committed after model validation | Agree
259 | MATAI STREET_6 | 6 | 206 | All | 2520 |  | Preseal_CS | 2025 | 18900 |  | accepted as committed after model validation
315 | QUEEN STREET_527 | 527 | 711 | All | 2576 |  | Preseal_AC | 2025 | 48944 |  | accepted as committed after model validation
208 | OPAKI KAIPARORO ROAD_24106 | 24106 | 24725 | All | 3775.9 |  | Preseal_CS | 2025 | 28319.25 |  | accepted as committed after model validation
288 | UPPER PLAIN ROAD_0 | 0 | 475 | All | 5747.5 |  | Preseal_CS | 2026 | 43106.25 |  | accepted as committed after model validation
338 | SOUTH ROAD URBAN_0 | 0 | 958 | All | 12454 |  | Preseal_CS | 2026 | 93405 |  | accepted as committed after model validation
371 | YORK STREET_89 | 89 | 458 | All | 4797 |  | Preseal_CS | 2026 | 35977.5 |  | accepted as committed after model validation
335 | SOLWAY CRESCENT_359 | 359 | 926 | All | 6237 |  | SecondCoat | 2026 | 61122.6 |  | accepted as committed after model validation
335 | SOLWAY CRESCENT_926 | 926 | 1136 | All | 2310 |  | SecondCoat | 2026 | 22638 |  | accepted as committed after model validation
446 | STONELEIGH DRIVE_7 | 7 | 297 | All | 2175 |  | SecondCoat | 2026 | 21315 |  | accepted as committed after model validation
462 | MITRE WAY_4 | 4 | 180 | All | 1320 |  | SecondCoat | 2026 | 12936 |  | accepted as committed after model validation
346 | TARANAKI STREET_325 | 325 | 595 | All | 2430 |  | SecondCoat | 2026 | 23814 |  | accepted as committed after model validation
116 | LEES PAKARAKA ROAD_2399 | 2399 | 3740 | All | 8046 |  | SecondCoat | 2026 | 78850.8 |  | accepted as committed after model validation
144 | TE WHITI ROAD_4955 | 4955 | 5206 | All | 1506 |  | SecondCoat | 2026 | 14758.8 |  | accepted as committed after model validation
116 | LEES PAKARAKA ROAD_73 | 73 | 1120 | All | 5235 |  | SecondCoat | 2026 | 51303 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_7553 | 7553 | 7840 | All | 2009 |  | SecondCoat | 2026 | 19688.2 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_54983 | 54983 | 55594 | All | 3910.4 |  | SecondCoat | 2026 | 38321.92 |  | accepted as committed after model validation
282 | TINUI VALLEY ROAD_5140 | 5140 | 7120 | All | 9504 |  | SecondCoat | 2026 | 93139.2 |  | accepted as committed after model validation
318 | WESTMERE ROAD_3460 | 3460 | 4420 | All | 5760 |  | SecondCoat | 2026 | 56448 |  | accepted as committed after model validation
404 | TE ORE ORE ROAD_1096 | 1096 | 2287 | All | 16316.7 |  | ChipSeal_P | 2024 | 91826.7 |  | accepted as committed after model validation
404 | TE ORE ORE ROAD_2287 | 2287 | 2347 | All | 420 |  | Rehab_AC_RM | 2024 | 122040 |  | accepted as committed after model validation
270 | TE ORE ORE BIDEFORD ROAD_5 | 5 | 50 | All | 315 |  | Rehab_AC_RM | 2024 | 149040 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_0 | 0 | 45 | All | 328.5 |  | Rehab_AC_RM | 2024 | 54360 |  | accepted as committed after model validation
363 | WAVELL CRESCENT_6 | 6 | 465 | All | 4131 |  | ChipSeal_P | 2024 | 21758.2 |  | accepted as committed after model validation
125 | GORT PLACE_5 | 5 | 64 | All | 413 |  | ChipSeal_P | 2024 | 3068.6 |  | accepted as committed after model validation
404 | TE ORE ORE ROAD_740 | 740 | 1096 | All | 4877.2 |  | ChipSeal_P | 2024 | 12169.9 |  | accepted as committed after model validation
404 | TE ORE ORE ROAD_356 | 356 | 740 | All | 5376 |  | ChipSeal_P | 2024 | 25993.9 |  | accepted as committed after model validation
404 | TE ORE ORE ROAD_40 | 40 | 296 | All | 3584 |  | ChipSeal_P | 2024 | 9689.9 |  | accepted as committed after model validation
95 | DIXON STREET_323 | 323 | 647 | All | 4212 |  | Rehab_AC_UH | 2024 | 1097044.8 |  | accepted as committed after model validation
370 | WRIGLEY STREET_7 | 7 | 350 | All | 4802 |  | ChipSeal_P | 2024 | 20512 |  | accepted as committed after model validation
95 | DIXON STREET_1648 | 1648 | 2267 | All | 8356.5 |  | ChipSeal_P | 2024 | 41896.5 |  | accepted as committed after model validation
147 | HIGH STREET (SH2)_0 | 0 | 176 | All | 2464 |  | ChipSeal_P | 2024 | 14288.4 |  | accepted as committed after model validation
361 | WALTONS AVE_0 | 0 | 95 | All | 1235 |  | ChipSeal_P | 2024 | 6739 |  | accepted as committed after model validation
33 | BLEDISLOE STREET_10 | 10 | 296 | All | 2631.2 |  | ChipSeal_P | 2024 | 14721.1 |  | accepted as committed after model validation
119 | FREYBERG STREET_5 | 5 | 291 | All | 2574 |  | ChipSeal_P | 2024 | 15093.1 |  | accepted as committed after model validation
153 | HOBSON PLACE_5 | 5 | 74 | All | 634.8 |  | ChipSeal_P | 2024 | 3713.8 |  | accepted as committed after model validation
107 | FERGUSSON STREET_5 | 5 | 479 | All | 4408.2 |  | ChipSeal_P | 2024 | 25827 |  | accepted as committed after model validation
137 | HARLEY STREET_6 | 6 | 1228 | All | 15152.8 |  | ChipSeal_P | 2024 | 143150 |  | accepted as committed after model validation
173 | JELLICOE PLACE_5 | 5 | 74 | All | 621 |  | ChipSeal_P | 2024 | 4478.9 |  | accepted as committed after model validation
419 | GIMSON STREET_419 | 419 | 809 | All | 3549 |  | ChipSeal_P | 2024 | 20007 |  | accepted as committed after model validation
448 | CRAIGMILLAR STREET_4 | 4 | 469 | All | 4185 |  | ChipSeal_P | 2024 | 24610.4 |  | accepted as committed after model validation
454 | WYCLIFFE PLACE_5 | 5 | 227 | All | 1998 |  | ChipSeal_P | 2024 | 12367.6 |  | accepted as committed after model validation
21 | BANNISTER STREET_130 | 130 | 925 | All | 11130 |  | ChipSeal_P | 2024 | 59398.9 |  | accepted as committed after model validation
368 | WORKSOP ROAD_140 | 140 | 525 | All | 5621 |  | ChipSeal_P | 2024 | 32153.5 |  | accepted as committed after model validation
368 | WORKSOP ROAD_525 | 525 | 922 | All | 5796.2 |  | ChipSeal_P | 2024 | 32907.1 |  | accepted as committed after model validation
124 | LOOPLINE_13 | 13 | 1956 | All | 10880.8 |  | ChipSeal_P | 2024 | 68801.9 |  | accepted as committed after model validation
214 | PAIERAU ROAD_293 | 293 | 993 | All | 4900 |  | ChipSeal_P | 2024 | 28611.3 |  | accepted as committed after model validation
214 | PAIERAU ROAD_993 | 993 | 2493 | All | 10500 |  | ChipSeal_P | 2024 | 66506.3 |  | accepted as committed after model validation
20 | BLUFF RANGITUMAU ROAD_4 | 4 | 1299 | All | 7640.5 |  | ChipSeal_P | 2024 | 38482.3 |  | accepted as committed after model validation
20 | BLUFF RANGITUMAU ROAD_1299 | 1299 | 2181 | All | 5292 |  | ChipSeal_P | 2024 | 20926.1 |  | accepted as committed after model validation
20 | BLUFF RANGITUMAU ROAD_2785 | 2785 | 3288 | All | 3018 |  | ChipSeal_P | 2024 | 20926.1 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_6600 | 6600 | 6800 | All | 1420 |  | ChipSeal_P | 2024 | 7860 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_6800 | 6800 | 7000 | All | 1420 |  | ChipSeal_P | 2024 | 6481.6 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_7000 | 7000 | 8330 | All | 9443 |  | ChipSeal_P | 2024 | 48758.1 |  | accepted as committed after model validation
52 | DITTON ROAD_4 | 4 | 667 | All | 2519.4 |  | ChipSeal_P | 2024 | 14617.9 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_8330 | 8330 | 9280 | All | 6080 |  | ChipSeal_P | 2024 | 36872.8 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_9280 | 9280 | 9416 | All | 816 |  | ChipSeal_P | 2024 | 4730.1 |  | accepted as committed after model validation
270 | TE ORE ORE BIDEFORD ROAD_19589 | 19589 | 20108 | All | 3114 |  | ChipSeal_P | 2024 | 17247.7 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_3932 | 3932 | 5260 | All | 8897.6 |  | ChipSeal_P | 2024 | 41993.4 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_10168 | 10168 | 10260 | All | 598 |  | Rehab_AC_RM | 2024 | 64800 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_13062 | 13062 | 13183 | All | 750.2 |  | Rehab_AC_RM | 2024 | 139986 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_14283 | 14283 | 15603 | All | 8184 |  | ChipSeal_P | 2024 | 38424.2 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_17224 | 17224 | 17775 | All | 3746.8 |  | Rehab_CS_RM | 2024 | 560732.2 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_23300 | 23300 | 23890 | All | 4012 |  | Rehab_CS_RM | 2024 | 318756.2 |  | accepted as committed after model validation
18 | BLAIRLOGIE LANGDALE ROAD_2844 | 2844 | 3742 | All | 6286 |  | ChipSeal_P | 2024 | 31288.5 |  | accepted as committed after model validation
32 | BUTE ROAD_1884 | 1884 | 2140 | All | 819.2 |  | Rehab_CS_RM | 2024 | 161030.8 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_48906 | 48906 | 49847 | All | 6210.6 |  | ChipSeal_P | 2024 | 28998.4 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_57460 | 57460 | 59910 | All | 13475 |  | ChipSeal_P | 2024 | 62750.7 |  | accepted as committed after model validation
148 | MATAIKONA ROAD_3902 | 3902 | 4299 | All | 1588 |  | ChipSeal_P | 2024 | 7462.8 |  | accepted as committed after model validation
148 | MATAIKONA ROAD_4299 | 4299 | 4514 | All | 860 |  | ChipSeal_P | 2024 | 3990.9 |  | accepted as committed after model validation
148 | MATAIKONA ROAD_11268 | 11268 | 11370 | All | 469.2 |  | ChipSeal_P | 2024 | 2147.1 |  | accepted as committed after model validation
148 | MATAIKONA ROAD_12493 | 12493 | 12635 | All | 511.2 |  | ChipSeal_P | 2024 | 2341 |  | accepted as committed after model validation
146 | MASTERTON STRONVAR ROAD_21912 | 21912 | 22600 | All | 4816 |  | ChipSeal_P | 2024 | 26668.3 |  | accepted as committed after model validation
208 | OPAKI KAIPARORO ROAD_13310 | 13310 | 13925 | All | 4059 |  | ChipSeal_P | 2024 | 19694.1 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_11300 | 11300 | 12623 | All | 7938 |  | ChipSeal_P | 2025 | 79380 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_12623 | 12623 | 13900 | All | 7662 |  | ChipSeal_P | 2025 | 76620 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_13900 | 13900 | 14200 | All | 1800 |  | ChipSeal_P | 2025 | 18000 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_14285 | 14285 | 15235 | All | 5700 |  | ChipSeal_P | 2025 | 57000 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_14200 | 14200 | 14285 | All | 510 |  | ChipSeal_P | 2025 | 5100 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_15235 | 15235 | 15800 | All | 3390 |  | ChipSeal_P | 2025 | 33900 |  | accepted as committed after model validation
405 | WHANGAEHU VALLEY ROAD_15800 | 15800 | 16300 | All | 3000 |  | ChipSeal_P | 2025 | 30000 |  | accepted as committed after model validation
270 | TE ORE ORE BIDEFORD ROAD_17970 | 17970 | 19330 | All | 7208 |  | ChipSeal_P | 2025 | 81600 |  | accepted as committed after model validation
270 | TE ORE ORE BIDEFORD ROAD_7020 | 7020 | 8392 | All | 8232 |  | ChipSeal_P | 2025 | 1120 |  | accepted as committed after model validation
270 | TE ORE ORE BIDEFORD ROAD_4616 | 4616 | 7020 | All | 17068.4 |  | ChipSeal_P | 2025 | 168280 |  | accepted as committed after model validation
270 | TE ORE ORE BIDEFORD ROAD_50 | 50 | 2086 | All | 14252 |  | ChipSeal_P | 2025 | 142870 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_10951 | 10951 | 11420 | All | 2907.8 |  | Rehab_CS_RM | 2025 | 290605 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_11900 | 11900 | 12330 | All | 2666 |  | Rehab_CS_RM | 2025 | 407009.4 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_12330 | 12330 | 12501 | All | 1060.2 |  | Rehab_CS_RM | 2025 | 407009.4 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_12880 | 12880 | 13062 | All | 1128.4 |  | ChipSeal_P | 2025 | 32100 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_13183 | 13183 | 13800 | All | 3825.4 |  | ChipSeal_P | 2025 | 32100 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_18663 | 18663 | 19442 | All | 5297.2 |  | Rehab_CS_RM | 2025 | 550765.6 |  | accepted as committed after model validation
18 | BLAIRLOGIE LANGDALE ROAD_3742 | 3742 | 4080 | All | 2366 |  | ChipSeal_P | 2025 | 29190 |  | accepted as committed after model validation
18 | BLAIRLOGIE LANGDALE ROAD_4080 | 4080 | 6380 | All | 16100 |  | ChipSeal_P | 2025 | 161000 |  | accepted as committed after model validation
18 | BLAIRLOGIE LANGDALE ROAD_6380 | 6380 | 8311 | All | 13517 |  | ChipSeal_P | 2025 | 35000 |  | accepted as committed after model validation
90 | HOMEWOOD ROAD_1655 | 1655 | 3280 | All | 9750 |  | ChipSeal_P | 2025 | 97500 |  | accepted as committed after model validation
32 | BUTE ROAD_8 | 8 | 1296 | All | 6440 |  | Rehab_CS_RM | 2025 | 481185.6 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_29550 | 29550 | 29918 | All | 2502.4 |  | ChipSeal_P | 2025 | 23628 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_29918 | 29918 | 30596 | All | 4474.8 |  | ChipSeal_P | 2025 | 44748 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_30596 | 30596 | 30700 | All | 686.4 |  | ChipSeal_P | 2025 | 6864 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_30700 | 30700 | 31550 | All | 5610 |  | ChipSeal_P | 2025 | 56100 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_31550 | 31550 | 31715 | All | 1089 |  | ChipSeal_P | 2025 | 10890 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_31715 | 31715 | 32287 | All | 3775.2 |  | ChipSeal_P | 2025 | 37752 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_32287 | 32287 | 33055 | All | 5068.8 |  | ChipSeal_P | 2025 | 50688 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_33055 | 33055 | 33282 | All | 1475.5 |  | ChipSeal_P | 2025 | 12210 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_45464 | 45464 | 46522 | All | 6136.4 |  | ChipSeal_P | 2025 | 61364 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_46522 | 46522 | 48906 | All | 15734.4 |  | ChipSeal_P | 2025 | 101500 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_49847 | 49847 | 50531 | All | 4514.4 |  | ChipSeal_P | 2025 | 45144 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_50531 | 50531 | 50827 | All | 1894.4 |  | ChipSeal_P | 2025 | 19536 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_50827 | 50827 | 51958 | All | 7238.4 |  | ChipSeal_P | 2025 | 72384 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_51958 | 51958 | 52135 | All | 1132.8 |  | ChipSeal_P | 2025 | 11328 |  | accepted as committed after model validation
398 | MASTERTON CASTLEPOINT ROAD 2_52135 | 52135 | 52389 | All | 1625.6 |  | ChipSeal_P | 2025 | 16256 |  | accepted as committed after model validation
144 | TE WHITI ROAD_3030 | 3030 | 3710 | All | 4080 |  | ChipSeal_P | 2025 | 40800 |  | accepted as committed after model validation
144 | TE WHITI ROAD_3710 | 3710 | 3990 | All | 1680 |  | ChipSeal_P | 2025 | 16800 |  | accepted as committed after model validation
144 | TE WHITI ROAD_3990 | 3990 | 4340 | All | 2100 |  | ChipSeal_P | 2025 | 21000 |  | accepted as committed after model validation
144 | TE WHITI ROAD_4340 | 4340 | 4955 | All | 3690 |  | ChipSeal_P | 2025 | 36900 |  | accepted as committed after model validation
144 | TE WHITI ROAD_5206 | 5206 | 5319 | All | 678 |  | ChipSeal_P | 2025 | 6780 |  | accepted as committed after model validation
144 | TE WHITI ROAD_6030 | 6030 | 7670 | All | 9840 |  | ChipSeal_P | 2025 | 98400 |  | accepted as committed after model validation
144 | TE WHITI ROAD_8200 | 8200 | 9099 | All | 5394 |  | ChipSeal_P | 2025 | 53940 |  | accepted as committed after model validation
144 | TE WHITI ROAD_10110 | 10110 | 10817 | All | 4242 |  | ChipSeal_P | 2025 | 42420 |  | accepted as committed after model validation
143 | HEREWINI STREET_6 | 6 | 305 | All | 4335.5 |  | ChipSeal_P | 2025 | 43355 |  | accepted as committed after model validation
143 | HEREWINI STREET_305 | 305 | 346 | All | 594.5 |  | ChipSeal_P | 2025 | 5950 |  | accepted as committed after model validation
309 | POWNALL STREET_0 | 0 | 579 | All | 6484.8 |  | ChipSeal_P | 2025 | 38077.6 |  | accepted as committed after model validation
309 | POWNALL STREET_579 | 579 | 775 | All | 2312.8 |  | ChipSeal_P | 2025 | 7674.4 |  | accepted as committed after model validation
315 | QUEEN STREET_976 | 976 | 1170 | All | 2716 |  | ThinAC_P | 2025 | 135800 |  | accepted as committed after model validation | note: is dependent on water main renewal
315 | QUEEN STREET_847 | 847 | 976 | All | 1806 |  | ThinAC_P | 2025 | 90300 |  | accepted as committed after model validation | note: is dependent on water main renewal
315 | QUEEN STREET_711 | 711 | 847 | All | 1904 |  | ThinAC_P | 2025 | 95200 |  | accepted as committed after model validation | note: is dependent on water main renewal
60 | DREYERS ROCK ROAD_4707 | 4707 | 6585 | All | 11268 |  | ChipSeal_P | 2026 | 112680 |  | accepted as committed after model validation
60 | DREYERS ROCK ROAD_3500 | 3500 | 4707 | All | 7242 |  | ChipSeal_P | 2026 | 72420 |  | accepted as committed after model validation
60 | DREYERS ROCK ROAD_2745 | 2745 | 3500 | All | 4530 |  | ChipSeal_P | 2026 | 12180 |  | accepted as committed after model validation
60 | DREYERS ROCK ROAD_2352 | 2352 | 2745 | All | 2358 |  | Rehab_CS_RM | 2026 | 200825.8 |  | accepted as committed after model validation
60 | DREYERS ROCK ROAD_1600 | 1600 | 2352 | All | 4512 |  | ChipSeal_P | 2026 | 23880 |  | accepted as committed after model validation
60 | DREYERS ROCK ROAD_1183 | 1183 | 1600 | All | 2502 |  | Rehab_CS_RM | 2026 | 176913.8 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_1620 | 1620 | 2140 | All | 3744 |  | Rehab_CS_RM | 2026 | 516880 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_2140 | 2140 | 2473 | All | 2397.6 |  | Rehab_CS_RM | 2026 | 330960 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_2473 | 2473 | 2538 | All | 435.5 |  | Rehab_AC_RM | 2026 | 114660 |  | accepted as committed after model validation
316 | WESTBUSH ROAD_5 | 5 | 3653 | All | 21888 |  | ChipSeal_P | 2026 | 222528 |  | accepted as committed after model validation
214 | PAIERAU ROAD_7052 | 7052 | 7734 | All | 4774 |  | Rehab_CS_RM | 2026 | 440216 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_9164 | 9164 | 9688 | All | 3510.8 |  | Rehab_CS_RM | 2026 | 210975.8 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_9688 | 9688 | 10025 | All | 2257.9 |  | SecondCoat | 2026 | 22127.42 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_10025 | 10025 | 10168 | All | 929.5 |  | SecondCoat | 2026 | 9109.1 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_10260 | 10260 | 10750 | All | 3038 |  | SecondCoat | 2026 | 29772.4 |  | accepted as committed after model validation
144 | TE WHITI ROAD_1185 | 1185 | 2059 | All | 5244 |  | Rehab_CS_RM | 2027 | 917700 |  | accepted as committed after model validation
144 | TE WHITI ROAD_498 | 498 | 1185 | All | 4465.5 |  | Rehab_CS_RM | 2027 | 781462.5 |  | accepted as committed after model validation
18 | BLAIRLOGIE LANGDALE ROAD_8311 | 8311 | 13037 | All | 33082 |  | ChipSeal_P | 2027 | 324203.6 |  | accepted as committed after model validation
142 | MASTERTON CASTLEPOINT ROAD_39742 | 39742 | 39800 | All | 382.8 |  | SecondCoat | 2027 | 3751.44 |  | accepted as committed after model validation
148 | MATAIKONA ROAD_3220 | 3220 | 3902 | All | 3410 |  | SecondCoat | 2027 | 33418 |  | accepted as committed after model validation