## pre-validation-decisions (4)
ElementName | TreatmentName | TreatmentCost | TreatmentPeriod | DecisionCode | Comment
MASTERTON CASTLEPOINT ROAD_15603 | Rehab_CS_RM | 589894.2 | 2 | accept | Condition data in RAMM is inaccurate
NEWALL PLACE_5 | Preseal_CS | 65929.5 | 2 | modify | Repair methodology to be re-considered- reduce actual cost
YORK STREET_0 | Preseal_CS | 17088 | 2 | accept | Agree
INTERMEDIATE STREET_6 | Preseal_CS | 41560.5 | 2 | accept
HOSKING PLACE_4 | Preseal_CS | 25110 | 2 | modify | MDC to check with services programme and confirm
COLE STREET_943 | Preseal_CS | 29979.75 | 2 | accept | Agree
GEORGE HERON PLACE_6 | Preseal_CS | 52920 | 2 | accept | Agree
KIBBLEWHITE ROAD_5 | Preseal_CS | 28231.5 | 2 | modify | MDC to look into drainage improvements on rural side
RAILWAY CRESCENT_7 | ChipSeal_H | 34316.66 | 3 | push_out | RP 0-160 existing surface is AC ; RP 160-368 existing surface is CS; Push both sections out 8yrs
RAILWAY CRESCENT_7 | Preseal_CS | 26262.75 | 2 | push_out | RP 0-160 Existing surface is AC; RP 160-368 existing surface is CS; Push pre-seal on both sections out 7 yrs
KITCHENER STREET_6 | Preseal_CS | 48937.5 | 2 | modify | Extend Kitchener St section right up to Gordon St
KITCHENER STREET_6 | ChipSeal_H | 63945 | 3 | modify | Extend Kitchener St section right up to Gordon St
MANUKA STREET_6 | Preseal_CS | 67230 | 2 | accept | Agree
MATAI STREET_6 | Preseal_CS | 18900 | 2 | accept
TITOKI STREET_6 | Preseal_CS | 13617 | 4 | modify | Bring forward to 2025/26 preseal alongside RP 335-620
TITOKI STREET_335 | Preseal_AC | 18411 | 2 | modify | Resurface will need to be CS in 26/27 - forced trigger; Combine with RP 0-273 CS section
KILMORY LANE_370 | Preseal_AC | 22344 | 2 | push_out | Push out 8 yrs
QUEEN STREET_452 | Rehab_AC_UM | 313200 | 2 | push_out | Funding allocated elsewhere
PERRY STREET CBD_4 | Preseal_AC | 10545 | 2 | modify | Rehab
BANNISTER STREET_6 | Preseal_AC | 20295.8 | 2 | modify | Rehab
CHAPEL STREET S.L. (LONGS)_6 | Preseal_AC | 15390 | 2 | modify | Move to year 3
CHAPEL STREET S.L. (TRUSTBANK)_6 | Preseal_AC | 7144 | 2 | modify | Move to year 3
CRICKET STREET_7 | Preseal_CS | 18067.5 | 2 | modify | Move to year 3 ; MDC to carry out stormwater improvements on intersection to Park St in year 2
QUEEN STREET_527 | Preseal_AC | 48944 | 2 | accept
CRICKET STREET_288 | Preseal_CS | 2880 | 2 | push_out | Push out 10 yrs; MDC to update top surface in RAMM
MASTERTON STRONVAR ROAD_6 | Preseal_AC | 21945 | 2 | modify | Committed section in year 3 rehab
WATSONS ROAD_3365 | Preseal_CS | 11550 | 2 | modify | Trigger the whole road
WATSONS ROAD_3365 | ChipSeal_H | 15092 | 3 | modify | Trigger the whole road
TE ORE ORE BIDEFORD ROAD_8447 | Preseal_CS | 20340 | 2 | push_out | Push to next NLTP
TE ORE ORE BIDEFORD ROAD_13698 | Preseal_CS | 30690 | 2 | modify | Push out to year three; MDC to look at drainage improvement work
OPAKI KAIPARORO ROAD_24106 | Preseal_CS | 28319.25 | 2 | accept
MASTERTON CASTLEPOINT ROAD_39742 | Rehab_CS_RM | 66990 | 2 | push_out | Push out 5yrs. Pavement has some rutting but can last another 5yrs
DIXON STREET_647 | Preseal_CS | 333333 | 3 | push_out | Why is this section being triggered - surface is less than 8yrs old | because it has 11.6% alligator cracking, lots of longitudinal cracking and very high traffic
RENALL STREET_955 | Preseal_AC | 164217 | 3 | push_out | Push out 10 yrs - Mostly reflective cracking
UPPER PLAIN ROAD_0 | Preseal_CS | 43106.25 | 3 | accept
SOUTH ROAD URBAN_0 | Preseal_CS | 93405 | 3 | accept
COCKBURN STREET_29 | Rehab_CS_UM | 312707.5 | 3 | modify | Preseal & reseal treatment
YORK STREET_89 | Preseal_CS | 35977.5 | 3 | accept
SOLWAY CRESCENT_359 | SecondCoat | 61122.6 | 3 | accept
SOLWAY CRESCENT_926 | SecondCoat | 22638 | 3 | accept
STONELEIGH DRIVE_7 | SecondCoat | 21315 | 3 | accept
MITRE WAY_4 | SecondCoat | 12936 | 3 | accept
OLD ORCHARD ROAD_6 | SecondCoat | 7921.34 | 3 | push_out | This is not a 2nd coat - RAMM data incorrect
ANDREWS STREET_0 | SecondCoat | 28314.16 | 3 | push_out | This is not a 2nd coat - RAMM data incorrect
ANDREWS STREET_466 | SecondCoat | 4010.16 | 3 | push_out | This is not a 2nd coat - RAMM data incorrect
TARANAKI STREET_325 | SecondCoat | 23814 | 3 | accept
LEES PAKARAKA ROAD_2399 | SecondCoat | 78850.8 | 3 | accept
TE WHITI ROAD_4955 | SecondCoat | 14758.8 | 3 | accept
LEES PAKARAKA ROAD_73 | SecondCoat | 51303 | 3 | accept
MASTERTON CASTLEPOINT ROAD_7553 | SecondCoat | 19688.2 | 3 | accept
MASTERTON CASTLEPOINT ROAD_10750 | Rehab_CS_RM | 218085 | 3 | push_out | Re-look in year 7
MASTERTON CASTLEPOINT ROAD_11809 | Rehab_CS_RM | 98735 | 3 | modify | Move to year 4 - check funding allocation in model for rehabs
MASTERTON CASTLEPOINT ROAD 2_61123 | Rehab_CS_RM | 349387.5 | 3 | modify | Move to year 4 - check fund allocation for rehabs in model
MASTERTON CASTLEPOINT ROAD 2_54983 | SecondCoat | 38321.92 | 3 | accept
TINUI VALLEY ROAD_5140 | SecondCoat | 93139.2 | 3 | accept
ANNEDALE ROAD_203 | Preseal_CS | 8262 | 3 | modify | MDC to field validate
BRUCE STREET_6 | Preseal_AC | 15903 | 3 | push_out | Push out 10yes -brick crossings causing fault triggers
WESTMERE ROAD_3460 | SecondCoat | 56448 | 3 | accept
TE ORE ORE ROAD_1096 | ChipSeal_P | 91826.7 | 1 | accept
TE ORE ORE ROAD_2287 | Rehab_AC_RM | 122040 | 1 | accept
TE ORE ORE BIDEFORD ROAD_5 | Rehab_AC_RM | 149040 | 1 | accept
MASTERTON CASTLEPOINT ROAD_0 | Rehab_AC_RM | 54360 | 1 | accept
WAVELL CRESCENT_6 | ChipSeal_P | 21758.2 | 1 | accept
GORT PLACE_5 | ChipSeal_P | 3068.6 | 1 | accept
TE ORE ORE ROAD_740 | ChipSeal_P | 12169.9 | 1 | accept
TE ORE ORE ROAD_356 | ChipSeal_P | 25993.9 | 1 | accept
TE ORE ORE ROAD_40 | ChipSeal_P | 9689.9 | 1 | accept
DIXON STREET_323 | Rehab_AC_UH | 1097044.8 | 1 | accept
WRIGLEY STREET_7 | ChipSeal_P | 20512 | 1 | accept
DIXON STREET_1648 | ChipSeal_P | 41896.5 | 1 | accept
HIGH STREET (SH2)_0 | ChipSeal_P | 14288.4 | 1 | accept
WALTONS AVE_0 | ChipSeal_P | 6739 | 1 | accept
BLEDISLOE STREET_10 | ChipSeal_P | 14721.1 | 1 | accept
FREYBERG STREET_5 | ChipSeal_P | 15093.1 | 1 | accept
HOBSON PLACE_5 | ChipSeal_P | 3713.8 | 1 | accept
FERGUSSON STREET_5 | ChipSeal_P | 25827 | 1 | accept
HARLEY STREET_6 | ChipSeal_P | 143150 | 1 | accept
JELLICOE PLACE_5 | ChipSeal_P | 4478.9 | 1 | accept
GIMSON STREET_419 | ChipSeal_P | 20007 | 1 | accept
CRAIGMILLAR STREET_4 | ChipSeal_P | 24610.4 | 1 | accept
WYCLIFFE PLACE_5 | ChipSeal_P | 12367.6 | 1 | accept
BANNISTER STREET_130 | ChipSeal_P | 59398.9 | 1 | accept
WORKSOP ROAD_140 | ChipSeal_P | 32153.5 | 1 | accept
WORKSOP ROAD_525 | ChipSeal_P | 32907.1 | 1 | accept
LOOPLINE_13 | ChipSeal_P | 68801.9 | 1 | accept
PAIERAU ROAD_293 | ChipSeal_P | 28611.3 | 1 | accept
PAIERAU ROAD_993 | ChipSeal_P | 66506.3 | 1 | accept
BLUFF RANGITUMAU ROAD_4 | ChipSeal_P | 38482.3 | 1 | accept
BLUFF RANGITUMAU ROAD_1299 | ChipSeal_P | 20926.1 | 1 | accept
BLUFF RANGITUMAU ROAD_2785 | ChipSeal_P | 20926.1 | 1 | accept
WHANGAEHU VALLEY ROAD_6600 | ChipSeal_P | 7860 | 1 | accept
WHANGAEHU VALLEY ROAD_6800 | ChipSeal_P | 6481.6 | 1 | accept
WHANGAEHU VALLEY ROAD_7000 | ChipSeal_P | 48758.1 | 1 | accept
DITTON ROAD_4 | ChipSeal_P | 14617.9 | 1 | accept
WHANGAEHU VALLEY ROAD_8330 | ChipSeal_P | 36872.8 | 1 | accept
WHANGAEHU VALLEY ROAD_9280 | ChipSeal_P | 4730.1 | 1 | accept
TE ORE ORE BIDEFORD ROAD_19589 | ChipSeal_P | 17247.7 | 1 | accept
MASTERTON CASTLEPOINT ROAD_3932 | ChipSeal_P | 41993.4 | 1 | accept
MASTERTON CASTLEPOINT ROAD_10168 | Rehab_AC_RM | 64800 | 1 | accept
MASTERTON CASTLEPOINT ROAD_13062 | Rehab_AC_RM | 139986 | 1 | accept
MASTERTON CASTLEPOINT ROAD_14283 | ChipSeal_P | 38424.2 | 1 | accept
MASTERTON CASTLEPOINT ROAD_17224 | Rehab_CS_RM | 560732.2 | 1 | accept
MASTERTON CASTLEPOINT ROAD_23300 | Rehab_CS_RM | 318756.2 | 1 | accept
BLAIRLOGIE LANGDALE ROAD_2844 | ChipSeal_P | 31288.5 | 1 | accept
BUTE ROAD_1884 | Rehab_CS_RM | 161030.8 | 1 | accept
MASTERTON CASTLEPOINT ROAD 2_48906 | ChipSeal_P | 28998.4 | 1 | accept
MASTERTON CASTLEPOINT ROAD 2_57460 | ChipSeal_P | 62750.7 | 1 | accept
MATAIKONA ROAD_3902 | ChipSeal_P | 7462.8 | 1 | accept
MATAIKONA ROAD_4299 | ChipSeal_P | 3990.9 | 1 | accept
MATAIKONA ROAD_11268 | ChipSeal_P | 2147.1 | 1 | accept
MATAIKONA ROAD_12493 | ChipSeal_P | 2341 | 1 | accept
MASTERTON STRONVAR ROAD_21912 | ChipSeal_P | 26668.3 | 1 | accept
OPAKI KAIPARORO ROAD_13310 | ChipSeal_P | 19694.1 | 1 | accept
WHANGAEHU VALLEY ROAD_11300 | ChipSeal_P | 79380 | 2 | accept
WHANGAEHU VALLEY ROAD_12623 | ChipSeal_P | 76620 | 2 | accept
WHANGAEHU VALLEY ROAD_13900 | ChipSeal_P | 18000 | 2 | accept
WHANGAEHU VALLEY ROAD_14285 | ChipSeal_P | 57000 | 2 | accept
WHANGAEHU VALLEY ROAD_14200 | ChipSeal_P | 5100 | 2 | accept
WHANGAEHU VALLEY ROAD_15235 | ChipSeal_P | 33900 | 2 | accept
WHANGAEHU VALLEY ROAD_15800 | ChipSeal_P | 30000 | 2 | accept
TE ORE ORE BIDEFORD ROAD_17970 | ChipSeal_P | 81600 | 2 | accept
TE ORE ORE BIDEFORD ROAD_7020 | ChipSeal_P | 1120 | 2 | accept
TE ORE ORE BIDEFORD ROAD_4616 | ChipSeal_P | 168280 | 2 | accept
TE ORE ORE BIDEFORD ROAD_50 | ChipSeal_P | 142870 | 2 | accept
MASTERTON CASTLEPOINT ROAD_10951 | Rehab_CS_RM | 290605 | 2 | accept
MASTERTON CASTLEPOINT ROAD_11900 | Rehab_CS_RM | 407009.4 | 2 | accept
MASTERTON CASTLEPOINT ROAD_12330 | Rehab_CS_RM | 407009.4 | 2 | accept
MASTERTON CASTLEPOINT ROAD_12880 | ChipSeal_P | 32100 | 2 | accept
MASTERTON CASTLEPOINT ROAD_13183 | ChipSeal_P | 32100 | 2 | accept
MASTERTON CASTLEPOINT ROAD_18663 | Rehab_CS_RM | 550765.6 | 2 | accept
BLAIRLOGIE LANGDALE ROAD_3742 | ChipSeal_P | 29190 | 2 | accept
BLAIRLOGIE LANGDALE ROAD_4080 | ChipSeal_P | 161000 | 2 | accept
BLAIRLOGIE LANGDALE ROAD_6380 | ChipSeal_P | 35000 | 2 | accept
HOMEWOOD ROAD_1655 | ChipSeal_P | 97500 | 2 | accept
BUTE ROAD_8 | Rehab_CS_RM | 481185.6 | 2 | accept
MASTERTON CASTLEPOINT ROAD_29550 | ChipSeal_P | 23628 | 2 | accept
MASTERTON CASTLEPOINT ROAD_29918 | ChipSeal_P | 44748 | 2 | accept
MASTERTON CASTLEPOINT ROAD_30596 | ChipSeal_P | 6864 | 2 | accept
MASTERTON CASTLEPOINT ROAD_30700 | ChipSeal_P | 56100 | 2 | accept
MASTERTON CASTLEPOINT ROAD_31550 | ChipSeal_P | 10890 | 2 | accept
MASTERTON CASTLEPOINT ROAD_31715 | ChipSeal_P | 37752 | 2 | accept
MASTERTON CASTLEPOINT ROAD_32287 | ChipSeal_P | 50688 | 2 | accept
MASTERTON CASTLEPOINT ROAD_33055 | ChipSeal_P | 12210 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_45464 | ChipSeal_P | 61364 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_46522 | ChipSeal_P | 101500 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_49847 | ChipSeal_P | 45144 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_50531 | ChipSeal_P | 19536 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_50827 | ChipSeal_P | 72384 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_51958 | ChipSeal_P | 11328 | 2 | accept
MASTERTON CASTLEPOINT ROAD 2_52135 | ChipSeal_P | 16256 | 2 | accept
TE WHITI ROAD_3030 | ChipSeal_P | 40800 | 2 | accept
TE WHITI ROAD_3710 | ChipSeal_P | 16800 | 2 | accept
TE WHITI ROAD_3990 | ChipSeal_P | 21000 | 2 | accept
TE WHITI ROAD_4340 | ChipSeal_P | 36900 | 2 | accept
TE WHITI ROAD_5206 | ChipSeal_P | 6780 | 2 | accept
TE WHITI ROAD_6030 | ChipSeal_P | 98400 | 2 | accept
TE WHITI ROAD_8200 | ChipSeal_P | 53940 | 2 | accept
TE WHITI ROAD_10110 | ChipSeal_P | 42420 | 2 | accept
HEREWINI STREET_6 | ChipSeal_P | 43355 | 2 | accept
HEREWINI STREET_305 | ChipSeal_P | 5950 | 2 | accept
POWNALL STREET_0 | ChipSeal_P | 38077.6 | 2 | accept
POWNALL STREET_579 | ChipSeal_P | 7674.4 | 2 | accept
QUEEN STREET_976 | ThinAC_P | 135800 | 2 | accept | note: is dependent on water main renewal
QUEEN STREET_847 | ThinAC_P | 90300 | 2 | accept | note: is dependent on water main renewal
QUEEN STREET_711 | ThinAC_P | 95200 | 2 | accept | note: is dependent on water main renewal
DREYERS ROCK ROAD_4707 | ChipSeal_P | 112680 | 3 | accept
DREYERS ROCK ROAD_3500 | ChipSeal_P | 72420 | 3 | accept
DREYERS ROCK ROAD_2745 | ChipSeal_P | 12180 | 3 | accept
DREYERS ROCK ROAD_2352 | Rehab_CS_RM | 200825.8 | 3 | accept
DREYERS ROCK ROAD_1600 | ChipSeal_P | 23880 | 3 | accept
DREYERS ROCK ROAD_1183 | Rehab_CS_RM | 176913.8 | 3 | accept
MASTERTON CASTLEPOINT ROAD_1620 | Rehab_CS_RM | 516880 | 3 | accept
MASTERTON CASTLEPOINT ROAD_2140 | Rehab_CS_RM | 330960 | 3 | accept
MASTERTON CASTLEPOINT ROAD_2473 | Rehab_AC_RM | 114660 | 3 | accept
WESTBUSH ROAD_5 | ChipSeal_P | 222528 | 3 | accept
PAIERAU ROAD_7052 | Rehab_CS_RM | 440216 | 3 | accept
MASTERTON CASTLEPOINT ROAD_9164 | Rehab_CS_RM | 210975.8 | 3 | accept
MASTERTON CASTLEPOINT ROAD_9688 | SecondCoat | 22127.42 | 3 | accept
MASTERTON CASTLEPOINT ROAD_10025 | SecondCoat | 9109.1 | 3 | accept
MASTERTON CASTLEPOINT ROAD_10260 | SecondCoat | 29772.4 | 3 | accept
WATSONS ROAD_7 | Preseal_CS | 302220 | 4 | modify | see year 2 comment bring forward to year 2
TOTARA STREET_715 | Rehab_CS_UH | 699930 | 4 | modify | change to AC surfacing
DIXON STREET_43 | Preseal_AC | 38570 | 4 | push_out | RAMM data not correct update surface life needed for AC layer
TE WHITI ROAD_1185 | Rehab_CS_RM | 917700 | 4 | accept
TE WHITI ROAD_498 | Rehab_CS_RM | 781462.5 | 4 | accept
BLAIRLOGIE LANGDALE ROAD_8311 | ChipSeal_P | 324203.6 | 4 | accept
MASTERTON CASTLEPOINT ROAD_39742 | SecondCoat | 3751.44 | 4 | accept
MATAIKONA ROAD_3220 | SecondCoat | 33418 | 4 | accept
MASTERTON CASTLEPOINT ROAD_1620 | SecondCoat | 36691.2 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_2140 | SecondCoat | 23496.48 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_10951 | SecondCoat | 28496.44 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_11900 | SecondCoat | 26126.8 | 4 | push_out
MASTERTON CASTLEPOINT ROAD_12330 | SecondCoat | 10389.96 | 4 | push_out